## Tally by RA
RA | Model | Assigned target (since 10/20) | Conversations in folder/sheet | New or re-collected since 10/28 (PDF created after 10/28 18:00 PT) | Counts now (Yes) | On hold – RA answer needed | Set aside (over target) | Pass | Fix | Redo/remove | Not submitted | Left to reach target | 10/28 Fix items now cleared | 10/28 Fix items still open | 10/28 Redo items now cleared | 10/28 Redo items still open
Lexi | GPT | 25 | 25 | 0 | 2 | 0 | 0 | 0 | 2 | 23 | 0 | 23 | 0 | 0 | 0 | 0
Lexi | Sonnet (Claude) | 28 | 28 | 24 | 5 | 22 | 0 | 5 | 22 | 1 | 0 | 1 | 0 | 0 | 0 | 0
Lexi | Gemini | 14 | 18 | 17 | 7 | 0 | 0 | 7 | 0 | 8 | 3 | 7 | 0 | 0 | 0 | 0
Lexi | Grok | 18 | 18 | 13 | 16 | 0 | 0 | 14 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0
Li Ke | GPT | 15 | 15 | 14 | 12 | 0 | 0 | 0 | 12 | 3 | 0 | 3 | 0 | 1 | 0 | 0
Li Ke | Sonnet (Claude) – not assigned (target 0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Li Ke | Gemini | 45 | 45 | 9 | 19 | 0 | 0 | 0 | 19 | 26 | 0 | 26 | 0 | 19 | 0 | 0
Li Ke | Grok | 25 | 12 | 3 | 10 | 0 | 0 | 4 | 6 | 2 | 0 | 15 | 0 | 6 | 0 | 0
Julia | GPT | 25 | 66 | 7 | 23 | 0 | 0 | 22 | 1 | 41 | 2 | 2 | 6 | 0 | 5 | 41
Julia | Sonnet (Claude) | 28 | 63 | 29 | 11 | 0 | 0 | 10 | 1 | 19 | 33 | 17 | 0 | 10 | 8 | 5
Julia | Gemini | 14 | 44 | 12 | 14 | 0 | 12 | 6 | 8 | 6 | 12 | 0 | 8 | 17 | 1 | 5
Julia | Grok | 18 | 13 | 1 | 3 | 0 | 0 | 3 | 0 | 10 | 0 | 15 | 1 | 0 | 1 | 10
Oswald | GPT | 35 | 35 | 10 | 35 | 0 | 0 | 27 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oswald | Sonnet (Claude) – not assigned (target 0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oswald | Gemini | 25 | 25 | 20 | 23 | 0 | 0 | 22 | 1 | 2 | 0 | 2 | 0 | 1 | 0 | 0
Oswald | Grok | 25 | 25 | 7 | 25 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Claire | GPT | 25 | 25 | 23 | 25 | 0 | 0 | 20 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Claire | Sonnet (Claude) | 28 | 25 | 2 | 24 | 0 | 0 | 23 | 1 | 1 | 0 | 4 | 0 | 0 | 0 | 0
Claire | Gemini | 13 | 25 | 11 | 13 | 0 | 11 | 13 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0
Claire | Grok | 19 | 25 | 5 | 19 | 0 | 6 | 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Dongli | GPT | 24 | 24 | 19 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dongli | Sonnet (Claude) | 28 | 28 | 21 | 19 | 5 | 0 | 0 | 24 | 4 | 0 | 4 | 0 | 4 | 0 | 0
Dongli | Gemini | 13 | 13 | 3 | 8 | 0 | 0 | 0 | 8 | 5 | 0 | 5 | 0 | 7 | 0 | 3
Dongli | Grok | 20 | 20 | 3 | 19 | 0 | 0 | 0 | 19 | 1 | 0 | 1 | 0 | 16 | 0 | 3
Total |  | 510 | 617 | 253 | 356 | 27 | 29 | 219 | 164 | 153 | 52 | 127 | 16 | 81 | 20 | 68

## By RA
RA | Target | Counts now (Yes) | On hold | Left to reach target | New/re-collected since 10/28 | Redo/remove now | Fix now | Not submitted | 10/28 items cleared | 10/28 items still open
Lexi | 85 | 30 | 22 | 33 | 54 | 32 | 26 | 5 | 0 | 0
Li Ke | 85 | 41 | 0 | 44 | 26 | 31 | 37 | 0 | 0 | 26
Julia | 85 | 51 | 0 | 34 | 49 | 76 | 10 | 47 | 30 | 88
Oswald | 85 | 83 | 0 | 2 | 37 | 2 | 9 | 0 | 0 | 1
Claire | 85 | 81 | 0 | 4 | 41 | 2 | 7 | 0 | 6 | 1
Dongli | 85 | 70 | 5 | 10 | 46 | 10 | 75 | 0 | 0 | 33